## Sheet1
Overall Implementation Plan |  |  | Project Engineering Gantt Chart
|  |  | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025
Project Management System | Work Content |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
| Initiation | Project Topic Selection | bar: March 2025 Week 1
Market Research | bar: March 2025 Week 2
Feasibility Analysis | bar: March 2025 Week 3
| Design | Hardware Selection and Procurement | bar: March 2025 Week 4 to April 2025 Week 1
Software Architecture Design | bar: April 2025 Week 1 to April 2025 Week 4
Deep Learning Model Development | bar: April 2025 Week 2 to May 2025 Week 1
| Integration | Hardware Assembly and Testing | bar: April 2025 Week 4 to May 2025 Week 4
Software Development and Integration | bar: April 2025 Week 4 to May 2025 Week 4
| Optimization | System Integration Testing | bar: May 2025 Week 3 to May 2025 Week 4
User Interface Design and Development | bar: May 2025 Week 3 to May 2025 Week 4
Project Optimization and Improvement | bar: May 2025 Week 3 to May 2025 Week 4
| Closing | Final Project Report and Documentation | bar: May 2025 Week 3 to June 2025 Week 2
Project Summary and Outcome Presentation | bar: May 2025 Week 4 to June 2025 Week 2